| Strengths | - Idea of the project; - Production of the different instruments; - Consortium always ready to find solutions together to keep the project moving; - Meet new people; - Comparative PE; - Aims of the project – comparison; - Implementation of the monitoring system and the webpage; - IO3 and IO4; - Multinational capacity of the team; - Project conceptually-rooted in ecological framework; - Big effort in formulating the IOs; - Constructive and vital debates on the instruments during the formulation; - Leadership and passion from the coordination; - Data from teachers and students; - Team quality; - Quality of the idea and the project; - Possibility to promote change in PE; - Capacity to adapt to the circumstances; - Common ground all of the times, even during the disagreement moments; - Placing at the fore the value of the project for the stakeholders; - Value of prolonged and sustained shared experience; - Building of critical mass for QPE; - UNESCO Meeting. |
| --- | --- |
| Weaknesses | - Disruption and uncertainty arising from corona; - Difference of the aspirations – coordination too much focused on the process development and needed a stronger orientation on the output; - Project timeline vs Educational timeline; - Balance between ambition and exhaustiveness of the elements to compile; - Communication; - With minimal resources there is low potential for national follow-up; - Not a complete European representation; - More research-based outputs to gather more attention from other countries; - Project management difficulties – more effective and pleasant communication; - Survey Burden – more from a complexity perspective than the length; - Need for a statistician support; - More support with the use of the funding; - Overly ambitious project; - Coordination took too much during many times in critical stages and found challenges in managing the meeting environment to a less work-intensive one - Too much repetition of previously discussed and decided ideas; - Challenge in managing different feedback and proposals within the consortium; - Coordination could have engaged better and clearer the partners; - Different levels of engagement between scientific and professional associations. |
| Suggestions of Improvement | - National network to start structuring a National Observatory; - Reduce the IOs 3 and 4 towards a sustainable process; - Detailed and clear idea based on the project application; - Clearer instructions; - More frequent meetings; - Include more countries in 2.0; - Better solution for feedback from youth; - More research outputs; - More statistical data-driven decisions; - Discuss how to implement the EuPEO; - More moments of contact between the consortium mixing face-to-face with online meetings; - Ensure that all partners understand all tasks/objectives at all stages; - Prepare the delivery to EUPEA. |